## Sheet1
Project Name | Domestic Migration in Germany
Project Acronym | DMIG
Project Manager | Adian Dawuda, Felix Schachtschneider
Project Deliverable | Dashboard, Code, and Documentation
Start Date | 2023-03-10
End Date | 31/01/2024
Overall Progress | 85%
[7 empty] | 02.10. - 08.10. | 09.10. - 15.10. | 16.10. - 22.10. | 23.10. - 29.10. | 30.10. - 05.11. | 06.11. - 12.11. | 13.11. - 19.11 | 20.11. - 26.11. | 27.11. - 03.12. | 04.12. - 10.12. | 11.12. - 17.12. | 18.12. - 24.12. | 25.12. - 31.12 | 01.01. - 07.01. | 08.01. - 14.01. | 15.01. - 21.01. | 22.01. - 28.01. | 29.01. - 31.01.
WP | Time Estimate (hours) | Tasks | Responsible | Start | End | Status | KW40 | KW41 | KW42 | KW43 | KW44 | KW45 | KW46 | KW47 | KW48 | KW49 | KW50 | KW51 | KW52 | KW01 | KW02 | KW03 | KW04 | KW05
1 | 20 (10%) | Project Management
1.1 | 10 | Establish project management procedures and documents | Adian, Felix | KW40 | KW46 | Complete | [6 empty] | ▪ | [11 empty] | ▪ | Deliverable
1.2 | 10 | Monitor and regularly update progress, milestones, and deliverables | Adian, Felix | KW40 | KW05 | Open | [8 empty] | ▪ |  | ▪ |  | ▪ |  | ▪ |  | ▪ | ▪ | ▫ | Milestone
2 | 30 (15%) | Literature Review & Methodology | [23 empty] | WP Duration
2.1 | 20 | State of the art literature review | Adian, Felix | KW40 | KW46 | Complete | [6 empty] | ▫ | [12 empty] | WT Duration
2.2 | 10 | Identify methodology | Adian, Felix | KW40 | KW46 | Complete | [6 empty] | ▪ | [12 empty] | WT Overdue
3 | 50 (30%) | Data Acquisition & Pre-Processing
3.1 | 10 | Set up computing environment | Adian, Felix | KW47 | KW48 | Complete | [8 empty] | ▫
3.2 | 20 | Collect raw data | Adian, Felix | KW48 | KW50 | Complete | [10 empty] | ▪
3.3 | 20 | Pre-process data | Adian, Felix | KW50 | KW51 | Complete | [11 empty] | ▪
4 | 60 (25%) | Data Processing & Analysis
4.1 | 20 | Insert data into PostGIS DB | Adian, Felix | KW51 | KW01 | Complete | [13 empty] | ▪
4.2 | 10 | Optimize PostGIS DB | Adian, Felix | KW52 | KW01 | Complete | [13 empty] | ▪
4.3 | 10 | Generate OGC services | Adian, Felix | KW02 | KW02 | Complete | [14 empty] | ▪
4.4 | 20 | Construct Dashboard | Adian, Felix | KW03 | KW04 | Complete | [16 empty] | ▪
5 | 40 (20%) | Dissemination
5.1 | 15 | Writing documentation (wiki) | Adian, Felix | KW46 | KW05 | Open | [16 empty] | ▪ | ▪
5.2 | 15 | Creating presentations | Adian, Felix | KW44 | KW05 | Open |  |  |  |  | ▪ |  |  |  | ▪ | [7 empty] | ▪ | ▪
5.3 | 10 | Publishing results | Adian, Felix | KW02 | KW05 | Open | [16 empty] | ▪ | ▪
|  | Completion |  |  | KW05